VOLUME 2

SECTION 3

SPECIAL CONDITIONS FOR EUROPEAN UNION EXTERNAL ACTIONS

# CONTENTS

# These conditions amplify and supplement the general conditions governing the contract. Unless the special conditions provide otherwise, the general conditions remain fully applicable. The numbering of the articles of the special conditions is not consecutive but follows the numbering of the general conditions. Exceptionally, and with the approval of the competent European Commission departments, other clauses can be indicated to cover particular situations.

# Contract value

# The contracting authority hereby agrees to pay to the contractor, in consideration of the execution and completion of the works and remedying of defects therein, the amount of the contract value mentioned in article 2 of the Main Conditions or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the contract. VAT will be paid in compliance with the binding regulations, national law and international agreements concerning the execution of the project.

# The amount of the contract value mentioned in article 2 of the Main Conditions shall be composed of:

- Contract price (excluding VAT/other taxes) EUR <amount>

The contract shall be exempt from all duties and taxes, including VAT.

# Order of precedence of contract documents

The following documents shall be deemed to form and be read and construed as part of this contract, in the following order of precedence:

- The main conditions

- the special conditions,

- the general conditions,

- the breakdown of lump-sum price (after arithmetical corrections)

- the technical and/or performance specifications,

- the design documentation (drawings),

- the tender,

- any other documents forming part of the contract.

The various documents making up the contract shall be deemed to be mutually explanatory; in cases of ambiguity or divergence, they shall prevail in the order in which they appear above. Addenda shall have the order of precedence of the document they are amending.

Termination clause

In addition to the grounds for termination defined in the General Conditions, this contract shall terminate automatically without liability to the Contracting Authority, upon the expiry or non-extension of the Mission’s mandate, as determined by the competent authority through the relevant official decision(s). Furthermore, the Contracting Authority may terminate the contract, in whole or in part, at any time after giving thirty (30) days’ notice to the Contractor, in case of budgetary issues affecting the implementation or financing of this contract.

In case of termination of the contract under this clause, the Contractor shall have the right to claim only the works duly executed and certified up to the effective date of termination of the contract. The Contractor shall NOT be entitled to claim any indemnity for loss suffered out of or in connection with such termination.

The Parties agree to the set of rights and obligations described in the attached contractual documents, with the following main characteristics, further detailed in the attachments:

|  |  |  | Contract-article: |
| --- | --- | --- | --- |
| 1 | Price | Lump sum contract | 49 |
|  |  | Prices cannot be revised | 48 |
| 2 | Duration | 18 months implementation of works from the commencement order | 34 |
|  |  | Provisional acceptance, after completion of works | 60 |
|  |  | Defects liability period of 365 days, after provisional acceptance | 61 |
|  |  | Final acceptance, after expiry of defects liability period | 62 |
| 3 | Delay | 0.1% of the contract price for every day of delay | 36 |
| 4 | Supervisor | Refer to special conditions of the contract | 5 |
| 5 | Bank guarantees | performance, pre-financing and retention guarantees are required | 15,46, 47 |
| 6 | Insurances | For damage to 3rd parties, unlimited for bodily injury | 16 |
|  |  | Contractor all risk insurance | 16 |
|  |  | Insurance against accidents at work | 16 |
|  |  | Insurance for soundness of works | 16 |
| 7 | Payments | lump sum advance for 10% of the original contract price, after conclusion of the contract | 46 |
|  |  | The minimum amount of each interim payment shall be 5% of the contract price, corresponding to the completion rate of the works confirmed by the Supervisor. | 49, 50 |
|  |  | Retention money for 10% of the contract price, after signed final statement of account | 47 |
| 9 | Working Hours | Monday to Thursday 09:00 – 17:00 hrs & Friday 08:00 – 15:45 hrs. | 9 |

Article 2	Language of the contract

2.1	The language used shall be English.

Article 4	Communication

4.1	Communication details

4.4    	Any written communication relating to this Contract between the Contracting Authority and/or the Project Manager, on the one hand, and the Contractor on the other must state the Contract title and identification number, and must be sent by post, e-mail or by hand.

For the Contracting Authority:

| Name: | EULEX Kosovo Attn: Project Manager |
| --- | --- |
| Address: | Lidhja e Pejës, Industrial Zone P.O. Box 268 10000 Pristina, Kosovo |
| E-mail: | XXXXXXXX |
| Mobile: | XXXXXX |

For the Contractor:

| Name: | XXXX Attn: XXXXX |
| --- | --- |
| Address: | XXXXX |
| E-mail: | XXXX |
| Landline: | XXXXX |
| Mobile: | XXXXXX |

Article 5	Supervisor and supervisor’s representative

5.1     The contracting authority shall appoint a supervisor (project manager) to carry out duties referred to in the contract. The supervisor may have further staff to which he delegates matters related to the contract.

The supervisor may issue to the contractor (at any time) instructions which may be necessary for the execution of works and the remedying of any defects, all in accordance with the contract. If an instruction constitutes a modification, Article 37 of General Conditions shall apply.

As established within Article 37 of the general conditions, administrative orders regarding the execution of the contract shall be given by the supervisor after due consultation with the contracting authority, such consultation may be conducted by e-mail, technical meetings and/or briefings on the status of the works.

5.2 	The supervisor shall obtain the formal approval of the contracting authority prior to taking the following action specified in the general conditions:

-	 any extension of time determined under Article 35 of the general conditions.

5.3     Administrative orders issued by the Supervisor shall be dated, numbered and delivered to the Contractor or its representative as specified under Article 4 above.

Article 7	Subcontracting

Subcontracting is allowed but the contractor will retain full liability towards the contracting authority for performance of the contract as a whole.

Article 8	Documents to be provided

8.1	All the drawings and documents related to this contract must strictly be treated as confidential by the Contractor, unless otherwise approved by the Contracting Authority in written.

Other drawings, calculations and technical documentation in addition to the ones contained in the tender dossier shall be submitted in the format and number required by the Supervisor.

Other drawings, calculations and technical documentation that the Contractor must provide to the Supervisor upon his request must be prepared and submitted within 7 calendar days from the date of such request. The Supervisor must approve, ask modifications or reject the presented documentation within 7 calendar days from the receiving date. Production of any documentation as may be requested from the Contractor shall be no subject to any additional claims in cost or extension of performance.

Article 9	Access to the site

9.1 	Access Permits: Access for all Contractor and subcontractor personnel (for site investigations, surveys, design, or construction) is strictly subject to site access permits issued by the Project Manager through administrative order. The Contractor shall submit all required personnel data in a timely manner.

Working Hours: Site access is restricted to standard working hours (Monday–Thursday: 09:00 – 17:00 hrs & Friday 08:00 – 15:45 hrs).

Work outside standard hours, including night shifts or weekends, requires prior written approval and an administrative order from the Supervisor upon a justified request by the Contractor.

Article 12	General obligations

12.9	The visibility measures must comply with the rules laid down in the Communication and Visibility Manual for EU External Actions published by the European Commission: Communicating and raising EU visibility - Guidance for external actions - July 2022_0.pdf (europa.eu)

Article 15	Performance guarantee

15.1	The amount of the performance guarantee will be 5 % of the amount of the contract and any addenda thereto.

Article 16	Liabilities and insurance

16.1 a)	By way of derogation from Article 16.1, a) paragraph 2, of the general conditions, compensation for damage to the works resulting from the contractor's liability in respect of the contracting authority is capped at an amount equal to the contract value.

16.1 b)	By way of derogation from Article 16.1, b), paragraph 2, of the general conditions, compensation for damage resulting from the contractor's liability in respect of the contracting authority is capped at an amount equal to the contract value.

Article 17	Programme of implementation of tasks

17.1 	The Contractor shall submit a detailed Programme of Implementation of the Tasks. The programme must include:

a) Sequence, dependencies, critical path, and timelines for design, approvals, procurement, construction, testing, training, and handover;

b) Design submittal and approval milestones;

c) Organization chart, site layout, and resource allocation schedules;

d) Alignment with payment tranches and progress milestones.

The Programme shall be developed with due consideration of the Preliminary Timeline provided by the Contracting Authority.

Review & Meetings: The Supervisor shall endorse or provide written remarks within 
10 calendar days of receipt, unless notifying the Contractor within this period that a technical meeting is required to discuss the submittal.

Article 19	Contractor’s drawings and execution studies

19.1  	The Contractor shall submit to the Supervisor for formal approval all preliminary and final designs, execution drawings, structural/geotechnical studies, and technical submissions:

a) Scope & Permits: Submissions must include all documentation required to secure statutory Building Permits, planning approvals, and utility connections, as well as for the complete execution and commissioning of the Works.

b) Timelines & Responsibility: Submissions shall adhere to the schedule and review gates in the approved Programme of Implementation (Article 17). The Contracting Authority bears full responsibility for the accuracy and completeness of permit applications submitted to municipal authorities.

c) Format & Details: Specific requirements regarding quantities, scales, formats, samples, or mock-ups are specified in the Technical Specifications.

19.7  	Manuals, drawing and any other document related to the performance of this contract must be in English.

Article 20	Sufficiency of tender prices

20.1	As this is a Lump Sum Contract, the Contractor shall understand that all works that are necessary to complete the facility and to bring it into a fully operational condition, shall be included into his tender price.

For this reason, the Contractor is required to visit the site with his experienced specialist staff, both for design and construction. Contractor shall be expected to study the conditions and to price the works with the reasonable skill and diligence that is to be expected of a competent Design/Build Contractor.

The Contractor shall be deemed to have satisfied himself as to the correctness and sufficiency of the Contract Price and to have based this on the data, interpretations, necessary information, inspections, examinations and his satisfaction as to all relevant matters that are necessary for the proper design and construction of the Works

No claims for extra payments due to other possible omissions in the tender document shall be entertained by the Contracting Authority.

Article 27	Demolished materials

27.1	All by-products classified and reported as Demolition by-products by the Supervisor on site shall be removed from the site by the contractor and disposed of in the municipal dump according to city regulations and standards for good practice.

Demolition by-products should be removed from the site as needed.

Article 34	Period of implementation of tasks

34.1 	Period after the effective date during which Contracting Authority’s representative must issue Administrative Order to commence the works within seven (7) calendar days from the contract signature.

The date of commencement shall be within be within fourteen (14) calendar days after issuing an administrative order (work order), notifying the Contractor of the date on which the period of implementation of tasks must start, but not before handing over the Insurance policy.

The period of the tasks will be eighteen (18) months from the commencement order.

Article 36	Delays in the implementation of tasks

36.1	The rate of liquidated damages for delays in the completion of works shall be 0.1% of the contract price for every day or part thereof which elapses between the end of the period of implementation of tasks and the actual date of completion, up to a maximum amount of 10 % of the contract price or, if the contract is subdivided into phases, 10 % of the price of the phase concerned.

Article 39	Work register

39.1	The Contractor shall maintain a Work Register (Contractor's Diary). The Work Register shall be kept in English Language on the site by the Contractor on daily basis, who shall enter in it at least the following information:

a) 	the weather conditions, interruptions of work owing to inclement weather, hours of work, number and type of workmen employed on the site, materials supplied, equipment in use, equipment not in working order, tests carried out in situ, samples dispatched, unforeseen circumstances, safety, health and welfare of persons and damage to property, progress of the works, as well as progress of the Works orders given to the Contractor;

b) 	detailed statements of all the quantitative and qualitative elements of the work done and the supplies delivered and used, capable of being checked on the site and relevant in calculating payments to be made to the Contractor. The statements shall be prepared by the Contractor, in accordance with the Technical Specifications.

Article 40	Origin and quality of works and materials

40.1	No rule of origin is applied.

Article 41	Inspection and testing

41	Inspection and testing shall be performed in accordance with the requirements of the technical specifications.

All materials and Equipment used are subject to inspection by the Supervisor.

Where the methods of tests are not specified in the standards, or if there are options in the relevant standards, the Contractor shall submit to the Supervisor for approval the methods by which he proposes to conduct the tests.

Article 43	Ownership of plant and materials

43.2	The equipment, temporary structures, plant and materials on the site shall for the duration of the execution of the works, be vested in the contracting authority.

Article 44:	General principles for payments

44.1	Payments shall be made in Euro.

44.2	Requests for payment shall be accompanied with an original invoice and must be addressed to the Contracting Authority through the Supervisor.

Payments shall be authorised and made by the Contracting Authority

44.3	By derogation, pre-financing payment to the Contractor for the lump-sum advance shall be made within 30 days. Other pre-financing payments to the Contractor shall be made within 90 days. Interim payments to the Contractor of the amounts due under each of the interim payment certificates approved by the supervisor shall be made within 90 days, and the final payment to the Contractor of the amounts due after the final statement of account issued by the Supervisor shall be made within 90 days.

Article 46	Pre-financing

46.1	Pre-financing is allowed.

46.2     	The total amount of the pre-financing must not exceed 10 % of the original contract price.

Where pre-financing is requested, the Contractor shall provide a financial guarantee for the full amount of the pre-financing payment (the contractor is not obliged to ask for pre-financing).

46.8	Repayment of the pre-financing shall take the form of deductions based on monthly claims.

- The flat-rate pre-financing (maximum of 10 %) shall be repaid by means of deductions from instalments and, if necessary, the balance due to the contractor. This repayment shall begin with the first instalment and be completed, at the very latest, by the time 80 % of the amount of the contract has been paid.

Repayment shall be made in the same currency as the pre-financing.

The amount to be deducted from each instalment shall be calculated using the following formula:

where:

R = the amount to be repaid

Va = the total amount of pre-financing

Vt = the initial contract amount

D = the amount of the instalment.

The result is rounded up to two decimal places.

- The pre-financing for plant, machinery and tools — and the pre-financing for other major prior outlays (20 % maximum) — shall be repaid by means of deductions from instalments and, if necessary, the balance due to the contractor. Repayment shall begin with the first instalment and end, at the very latest, by the time 90 % of the amount of the contract has been paid.

The amount to be deducted from each instalment shall be calculated using the following formula:

where:

R = the amount to be repaid

Va = the total amount of pre-financing

Vt = the initial contract amount

D = the amount of the instalment.

Article 47	Retention monies

47.1	The sum retained to guarantee the implementation of the Contractor's obligations during the Defects Liability Period shall be equal to 10% of the Contract Price.

By derogation from Article 47.1 of the General Conditions, such amount shall not be retained from interim payments. Instead, the Contractor shall provide, no later than the issuance of the Provisional Acceptance Certificate, a Retention Guarantee, in a form and by a financial institution acceptable to the Contracting Authority, for an amount equal to 10% of the Contract Price.

The Retention Guarantee shall remain valid until the expiry of the Defects Liability Period and the issuance of the Final Acceptance Certificate, upon which it shall be released.

Article 48	Price revision

48.1	Prices are fixed and shall not be revised.

Article 49	Measurement

49.1 	This is a Lump-Sum Contract.

The amounts due to the Contractor shall be calculated on the basis of the verified percentage of completion of each activity or stage of the Works, as defined in the approved Breakdown of the Lump-Sum Contract Price and corresponding payment tranches.

The percentage of completion shall be determined by the Supervisor on the basis of actual progress achieved and the fulfilment of the corresponding milestones, deliverables and obligations under the Contract, including design, procurement, construction, testing, commissioning, training and handover, as applicable.

The aggregate value of certified payments shall not exceed the Contract Price.

Article 50	Interim payments

50.1  	Requests for interim payment shall be submitted in accordance with the periods and milestones set out in the approved Programme of Implementation.

At the end of each relevant period or upon achievement of the corresponding milestone, the Contractor shall submit an Application for Interim Payment to the Supervisor, supported by progress reports and any documentation necessary to verify the value of the completed Works.

The minimum amount of each interim payment shall be 5% of the Contract Price, corresponding to the percentage of completion of the Works certified by the Supervisor.

The Supervisor may withhold the issue of an Interim Payment Certificate where the Works, or any part thereof, are not being carried out in accordance with the Contract or are otherwise unsatisfactory.

No Interim Payment Certificate shall be issued where the net certified value of completed Works is less than 5% of the Contract Price. Any amount below this threshold shall be carried forward and included in the next payment application.

Article 51	Final statement of account

51.1	The contractor shall, submit to the supervisor a draft final statement of account when it applies for the final acceptance certificate. In order to enable the supervisor to prepare the final statement of account, the draft final statement of account is submitted with supporting documents showing in detail the value of the work done in accordance with the contract and all further sums which the contractor considers to be due to it under the contract.

51.2	Within 30 days from issuing the final acceptance certificate referred to in Article 62, the supervisor shall prepare and signed the final statement of account.

Article 53	Delayed payments

53.1	By derogation from Article 53.1 of the general conditions, once the time-limit referred Article 44.3 has expired, the contractor shall be entitled to late-payment interest at the rate and for the period mentioned in the general conditions.

However, when the interest calculated in accordance with the first subparagraph is lower than or equal to EUR 200, it shall be paid to the creditor only upon a demand submitted within two months of receiving late payment.

Article 60	Provisional acceptance

60.1	In complement to Article 60.1 of the general conditions.

Article 61	Defects liability

61.1 	The defects liability period is defined as the period commencing on the date of provisional acceptance, during which the contractor is required to make good any defect in, or damage to, any part of the work which may appear or occur during this period as notify by the supervisor or the contracting authority. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the general conditions.

Article 68	Dispute settlement

68.1     Any dispute arising out of or relating to this contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of the courts of Brussels, Belgium.

Article 72	Data protection

For the purpose of Article 72 of the general conditions, for the part of the data transferred by the contracting authority to the European Commission:

- the controller for the processing of personal data carried out within the Commission is (FPI) is: The Head of Unit of FPI.6.

- the privacy statement is available at link.

1. Processing of personal data related to this tender procedure, launched by the CSDP Mission acting as the contracting authority, takes place in accordance with Council Decision (CFSP) 2025/1161 which established the Mission and with the provisions of the respective contribution agreement (CFSP) 2025/1161/EULEX Kosovo concluded between the European Commission and the Mission.

2. The tender procedure and the resulting contract relate to the implementation of an external action funded by the EU, represented by the European Commission.

3. Your reply to the invitation to tender may involve the transfer of personal data (such as names, contact details and CVs) from the CSDP Mission (being the contracting authority), to the European Commission. In such case, personal data shall be processed solely for the purposes of the monitoring of the procurement procedure and of the execution of the resulting contract, in line with the respective contribution agreement concluded with the CSDP Mission and with the Council Decision (CFSP) 2025/1161 which established the Mission. This is without prejudice to their possible transmission to the bodies in charge of monitoring or inspection tasks in application of EU law.

4. Details concerning the processing of your personal data by the contracting authority (the Mission) are available on the Mission’s privacy statement at ANNEX V: EULEX KOSOVO PRIVACY STATEMENT – DATA PROTECTION NOTICE.

The controller for the processing of personal data carried out within the contracting authority is: the Head of Mission of the CSDP Mission acting here as the contracting authority.

5. To the extent that the contract covers an action financed by the European Union, the contracting authority (the CSDP Mission) may share communications related to the implementation of the contract with the European Commission. These exchanges shall take place with the Commission, solely for the purpose of allowing the latter to exercise its rights and obligations under the applicable legislative framework and under the contribution agreement concluded with the Mission (the latter being the contracting authority for this contract).

6. These exchanges may involve transfers of personal data (such as names, contact details, signatures and CVs) of natural persons involved in the implementation of the contract (such as contractors, staff, experts, trainees, subcontractors, insurers, guarantors, auditors and legal counsels).

7. In cases where the contractor is processing personal data in the context of the implementation of the contract, he/she shall accordingly inform the data subjects of the possible transmission of their data to the Mission.

8. When personal data is transmitted by the contracting authority (the Mission) to the European Commission, the latter processes them in accordance with the contribution agreement concluded with the Mission, with Regulation (EU) 2018/1725 of the European Parliament and of the Council of 23 October 2018 on the protection of natural persons with regard to the processing of personal data by the Union institutions, bodies, offices and agencies and on the free movement of such data, and repealing Regulation (EC) No 45/2001 and Decision No 1247/2002/EC2 and as detailed in the following FPI privacy statement: Privacy Statement indirect management.pdf.

***

EULEX Kosovo is a diplomatic mission and according to UNMIK Executive Decision No 2008/36 of 9 December 2008, it is granted exemption from all customs duties, taxes, and related charges other than charges for storage, cartage and similar services, on articles for its official use.