## Summary
Construction of New ECM - Design and Build Project
Volume 4.2.2 Financial Offer - Summary
# | Description | Total amount
Designs development
1 | Preparation of designs - all disciplines
Infrastructure / Horizontal Services and Helipad
2 | Infrastructure / Horizontal Services and Helipad works
Vehicle and Pedestrian Main Entrance
3 | Provision of materials, Installation and Construction of Vehicle and Pedestrian Main Entrance including all security systems, as per designs and technical specifications requirements
Container blocks
4 | Provision of materials and construction of Platoon Accomodation Block #1, 2 and 3 as per designs and Technical Specifications requirements - same design and setup all three buildings
5 | Provision of materials and construction of the Female Accomodation Block #04 as per designs and Technical Specifications requirements
6 | Provision of materials and contruction of Commander Accomodation Block #05 as per designs and Technical Specifications requirements
7 | Provision of materials and construction of the Office Block #06 as per designs and Technical Specifications requirements
8 | Provision of materials and construction of the FPU Storage #07 as per designs and Technical Specifications requirements
9 | Provision of materials and construction of the MSO Block #12 as per designs and Technical Specifications requirements
10 | Provision of materials and construction of the Reception Block #13 as per designs and Technical Specifications requirements
11 | Provision of materials and construction of the Infirmary Block #14 as per designs and Technical Specifications requirements
12 | Provision of materials and construction of the Reserve Block #15 as per designs and Technical Specifications requirements
13 | Provision of materials and construction of the cleaning staff block #17 as per designs and Technical Specifications requirements
Total Container blocks - point 4 up to and including 13
Cafeteria
14 | Provision of materials and construction of Cafeteria Building, bld#11 as per designs and Technical Specifications requirements
15 | Provide and Install Kitchen appliances
Total Cafeteria (14+15)
Gym, Training House and Recreational Building
16 | Provision of materials and construction of Gym, bld #10 as per designs and Technical Specifications requirements
17 | Outdoor GYM and Court installations
18 | Provision of materials and construction of Training House, bld #09 as per designs and Technical Specifications requirements
19 | Provision of materials and construction of FPU Recreation building, bld#08 as per designs and Technical Specifications requirements
Total Gym, Training and Recreation- point 16 up to and including 19
MSD Building modification and refurbishment works (existing building)
20 | Provision of materials and refurbishment of MSD building, bld#16 as per designs and Technical Specifications requirements
21 | Provision of materials and construction of Vehicle Inspection Pit
Total MSD (20+21)
Electrical Intallations
22 | Provision of materials and electrical installation works for the whole Compound
CIS ( IT, COMMS, CCTV)
23 | Provision of materials and installation works for the complete New ECM ( IT, COMMS, CCTV)
Mechanical (HVAC)
24 | Provision of materials, ground and installation works for Heating and Ventilation Systems
Plumbing
25 | Provision of materials, ground and installation works for plumbing works ( water, sewerage, drainage and rainwater collection) for complete New ECM
Firefighting
26 | Provision of materials and installation works for File Alarm System for the complete new ECM
27 | Provision of materials ground and installation works for External Hydrants for the complete new ECM
Solar Panels
28 | Provision of materials and installation of Solar panels system complete - 260kWp capacity - Grid tied solar system with zero export device.
Fuel station
29 | Provision of materials and construction works for the setup of the Fuel Station
Other
30.1 | Covered parkings and other works
Dismantling of Container blocks and refurbishment of structure
31 | Dismantling of two container blocks in the old ECM and refurbishment of steel structures
SUMMARY - TOTAL LUMP SUM PRICE
Note: | This Summary presents Total "LUMP SUM" for Project Design and Build of New ECM.
The item description given in the breakdown of the lump-sum price in no way limits the contractor’s obligations under the contract to provide all the works described elsewhere.
The prices shall be exempt from all duties and taxes, including VAT .

## Designs
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - #01 Designs development
1 | Description | Unit | Quantity | Unit price | Total
Design Services
1.1 | Architectural Designs - develop further from the provided conceptual and preliminary designs | LS | 1
1.2 | Civil Engineering and Structural Designs
1.3 | Mechanical Designs (HVAC)
1.4 | Electrical Designs
1.5 | IT and Communication Designs
1.6 | Plumbing Designs ( water/sewerage/drainage/rainwater collection and reuse)
1.7 | Fire Alarm System Design
1.8 | Firefighting network - external hydrants designs
1.9 | Solar photovoltaic system design
Total #01
Note: | Please refer to Technical Specifications for details of all disciplines requirements
General Preliminary and Conceptual designs are provided as part of the dwg set
After approval of final designs by Contracting Authority as developed works can commence on site

## Infrastruc
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - #02 Infrastructure/Horizontal Services and Helipad works
2 | Description | Unit | Quantity | Unit price | Total
2.1 | Provision of materials and execution of ground works for trenches for Electrical/CIS/FireAlarm/SolarPanels. See technical specifications for details. Price to Include excavation, backfilling, sand, gravel, compaction, manholes with cover and color coded tape. Refer to technical specifications point 4.3 for details and preliminary dwg indicating the route of installations. Same route is proposed to used for all these installations, subject to final designs. | LS | 1
2.2 | Provision of materials and installation of underground/overground exterior ducting pipes for Electrical/CIS/FireAlarm/Solar Panels plus at least one empty pipe at each trench as reserve after final designs. Refer to technical specifications point 4.3 for details and preliminary dwg. Same routing is proposed to be used for all these installations, subject to final designs. | LS | 1
2.3 | Provision of materials and execution of works - curbstones various section 20/8, 25/8cm. | LS | 1
2.4 | Provision of materials and execution of works for roads, parking with curbstones of various section, 24/18-12cm or 24/18-15cm. | LS | 1
2.5 | This position is to include final preparation prior to paving/asphalting the area with provision of min 20cm of gravel for the road or 5cm of sand for the pavement as required under the final layers. Preparation works, final leveling compaction for asphalting and paving works. Refer to technical specifications point 4.3. | LS | 1
2.6 | Provision of materials and execution of works for all the sidewalks, secondary roads and utilities areas. Laying of pavement blocks dim 10x20x8cm. See technical specifications for details | LS | 1
2.7 | Provide and spread river washed stones around the buildings/ blocks strip sorrounding area- th=20cm | LS | 1
2.8 | Cutting of existing asphalt on site for connection of existing asphalt area with new area to be asphalted along the whole length. | LS | 1
2.9 | Provision of materials and asphalting works for the compound (roads, parking, helipad and other areas to be asphalted. Asphalting with mixture AB 16 in thickness of 8cm. See technical specifications for details and site layout for area to be asphalted. Note price to include also asphalting of trenches withing existing asphalted area. | LS | 1
2.1 | Provision of materials and execution of works for green areas, including planting. See technical specifications for details. | LS | 1
2.11 | Provision of materials and execution of works for all ground marking with traffic zone marking paint, two component, chlorinated solvent base type | LS | 1
2.12 | Installation of T walls around Helipad Area, as per situation plan. T walls 3 meter height to be provided by EULEX and aligned on site by contractor. | LS | 1
2.13 | Installation of Jersey barriers around Helipad area as per situation plan. Jersey barriers to be provided by EULEX. | LS | 1
2.14 | Install windsock pole for Helipad, which is to be provided by EULEX. Contractor in his price to include foundation and anchoring. | EA | 1
2.14 | Provision of materials and construction of reinforced concrete base for Containerised Data Center including grounding. Dim of DataCenter which is provided by EULEX are 605x244cm concrete base is to be at least 10cm wider on all sides, with 10cm level over the paved utility area | LS | 1
2.15 | Provision of materials and construction of reinforced concrete basis for 2X containerised backup generators ( dim of each 605x244cm) concrete base is to be at least 10cm wider on all sides, with 10cm level over the paved utility area | LS | 1
Total #02
Note: | T walls and Jersey bariers to be installed around the Helipad will be provided and transported on site by EULEX.
Trenches/manholes for Plumbing, Heating, Hydrants are not part of this breakdown. Price to be included under Plumbing, Mechanical and Hydrants breakdown - subject to designs for those phases/pipes routing.

## Entrance
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - #03 Vehicles and Pedestrians Main Entrance
3 | Description | Unit | Quantity | Unit price | Total
Security Systems / Vehicle and Pedestrian Entry
3.1 | Design, provide and install hi security bi folding gate (automated) as per technical specifications minimum set requirements. Free opening - 6 meters when both opened (2x3m). The gate is to be operated from Reception by the guard. Wings are to be able to function individually, separate motors. 3 meters entry/3meters exit. Price to include all required accessories, sensors, traffic lights, control panels, trenches and other for full functionality of the gate. | EA | 1
3.2 | Provide and install pedestrian metal bar door dim 210x100cm as per specifications provided, equipped with hydraulic door closure. | EA | 2
3.3 | Provide material, manufacture and install metal fence h=3m as per dwg provided. See technical specifications and dwg for details. Price to include V Profiles and concertina wire on top. Quantity estimated as per preliminary designs 160m' | LS | 1
3.4 | Provide material and install polycarbonate cover over the new installed fences as per the designs and specifications provided. Quantity estimated as per preliminary designs: 480m2 | LS | 1
3.5 | Design, provide and install Under Vehicle Survaillance System - UVSS completed set, including as well plate numbers recognition system/cameras. Check preliminary layout and technical specifications for all the technical details and requirements for detailed designs and installations. Price to include trenches/manholes or any other work/material provision for full functionality of the system. | Set | 1
3.6 | Provide and install delta road blocker, positioned as per preliminary designs provided. Raised height 0.8-1m, lenght 5m. See technical specs for details. Note that delta road blocker among others requires connection to the drainage system with manhole with pump. Price is to include the complete set as per techncial specifications, works, trenches and any other materials required for the system to be fully operational | EA | 1
3.7 | Provide and install road barriers 3.3 -3.5m length. See technical specifications for more details. | EA | 2
3.8 | Provide material and install Inox poles 10x10 cm for positioning of card readers h=1.2m, anchored in concrete foundation. | EA | 2
3.9 | Provision and installation of card readers complete set for entry and exit of the vehicles, guard in reception integrated with the entry system as per technical specifications. | SET | 2
3.1 | Provision and installation of card readers (in and out) for both pedestrian doors including card reader x 2 (in and out), electromagnet / electric lock, switch controlled from reception/guard . | SET | 2
3.11 | Provide and install video intercome set for the main pedestrian door with monitor located at reception | EA | 1
3.12 | Design, manufacture and install steel roof cover for the entrance as per technical specifications. Dimensions of the area to be covered 22x7.5m. Minimum clear height 460cm | LS | 1
3.13 | Provide and install steel angle impact barrier 500mm x 500x500 | EA | 2
3.14 | Provide and install steel Impact barrier 500mmx1000mm | EA | 4
Total #03
Note: Asphalting/pavement works to be included under infrastructure/ horizontal services works.
Provision of all materials/works/manpower for installation of above listed equipments and functionality are to be included under this breakdown

## Container Blocks
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - Container Blocks construction works
4 | Description | Unit | Quantity | Unit price | Total
Container Blocks # 1,2 &3 - Platoon Accomodation Blocks (identical all three blocks)
4.1 | Provision of materials and construction of foundation & grounding works for the container blocks. Unit Price: Lum Sum per block. | LS | 3
4.2 | Provision of materials and construction/Installation works of containers frames: including floor layers, walls & ceiling panels complete as per building layouts. Note: Container steel frames only creating the structure of the block will be provided by EULEX for all three blocks . Wall panels, ceiling panels, floor layers complete are to be included in this position as per technical specifications. Unit Price: Lump Sum per block | LS | 3
4.3 | Provision of materials and construction of flooring and ceiling works (structure and all layers) in corridors including internal and external staircases. Unit Price: Lump Sum per Block | LS | 3
4.4 | Provision of materials and installation of all doors and windows. Unit Price: Lump Sum per Block | LS | 3
4.5 | Provision of materials and execution of works for block roof cover complete as per technical specifications.. Unit Price: Lump sum per block. | LS | 3
4.6 | Provision of materials and execution of facade Insulation works as per technical specifications. Unit Price: Lump Sum per block | LS | 3
4.7 | Provision of materials and construction/ installation works in ablution units ,complete setup as per preliminary designs provided including partitions sanitary, boilers and other elements. Note: Sewerage and water network piping installation is included under plumbing BOQ up to each required connection. 4x20' ablution units in one block. Unit price: Lump Sum per ablution, including all 3 blocks (4x3=12). | EA | 12
4.8 | Provide materials/manufacture and install entry stairs with cover and ground floor emergency exit stair as required from the ground level. See technical Specificatons for details. Price per block. | LS | 3
4.9 | Provide and Install AC Unit Inverter of 12000 BTU. Refer to technical specifications for details - Total for three block | EA | 44
4.1 | Provide and Install AC Unit Inverter of 9000 BTU. Refer to technical Specifications for details - total for three blocks | EA | 32
Total #04 ( all 3 container blocks)
5 | Description | Unit | Quantity | Unit price | Total
Container Blocks # 4 - Female Accomodation Block
5.1 | Provision of materials and preparation of foundation & grounding works for the container blocks. | LS | 1
5.2 | Provision of materials and construction/Installation works of containers including floor, walls & ceiling panels complete. Note: Containers steel frames only creating the structure of the block all will be provided by EULEX . See technical specifications for all details. | LS | 1
5.3 | Provision of materials and construction of flooring and ceiling works in corridors ( structures and all layers) including internal and external staircases. | LS | 1
5.4 | Provision of materials and installation of all doors and windows. | LS | 1
5.5 | Provision of materials and execution of works for block roof cover as per technical specifications. | LS | 1
5.6 | Provision of materials and execution of facade Insulation works as per technical specifications. | LS | 1
5.7 | Provision of materials and construction/ installation works in small ablution units (complete setup as per preliminary designs provided including partitions sanitary, boilers and other elements. Note: Sewerage and water network piping installation is included under plumbing BOQ up to each required connection. Price per ablution unit. | EA | 4
5.8 | Provide materials/manufacture and install entry stairs with cover and ground floor emergency exit stair as required from the ground level. See technical Specificatons for details. Price per block. | LS | 1
5.9 | Provide and Install AC Unit Inverter of 9000 BTU. Refer to technical specifications for details. | EA | 10
Total #05
6 | Description | Unit | Quantity | Unit price | Total
Container Blocks # 5 - Commanders Accomodation Block
6.1 | Provision of materials and preparation of foundation & grounding works for the container blocks. | LS | 1
6.2 | Provision of materials and construction/Installation works of containers including floor, walls & ceiling panels complete. Note: Container steel frames only creating the structure of the block all will be provided by EULEX . See technical specifications for all details. | LS | 1
6.3 | Provision of materials and construction of flooring and ceiling works in corridors ( structure and all layers) including internal and external staircases. | LS | 1
6.4 | Provision of materials and installation of all doors and windows. | LS | 1
6.5 | Provision of materials and execution of works for block roof cover as per technical specifications. | LS | 1
6.6 | Provision of materials and execution of facade Insulation works as per technical specifications. | LS | 1
6.7 | Provision of materials and construction/ installation works in small ablution units (complete setup as per preliminary designs provided including partitions sanitary, boilers and other elements. Note: Sewerage and water network piping installation is included under plumbing BOQ up to each required connection. Price per ablution unit. | EA | 4
6.8 | Provide materials/manufacture and install entry stairs with cover and ground floor emergency exit stair as required from the ground level. See technical specificatons for details. | LS | 1
6.9 | Provide and Install AC Unit Inverter of 12000 BTU - Refer to technical Specifications for details. | EA | 5
6.1 | Provide and Install AC Unit Inverter of 9000 BTU - Refer to technical Specifications for details | EA | 4
Total #06
7 | Description | Unit | Quantity | Unit price | Total
Container Blocks # 6 - Office Block
7.1 | Provision of materials and preparation of foundation & grounding works for the container blocks. | LS | 1
7.2 | Provision of materials and construction/Installation works of containers including floor, walls & ceiling panels complete. Note: Container steel frames only creating the structure of the block all will be provided by EULEX . See technical specifications for all details. | LS | 1
7.3 | Provision of materials and construction of flooring and ceiling works in corridors ( structure and all layers) including internal and external staircases. | LS | 1
7.4 | Provision of materials and installation of all doors and windows. | LS | 1
7.5 | Provision of materials and execution of works for block roof cover as per technical specifications. | LS | 1
7.6 | Provision of materials and execution of facade Insulation works as per technical specifications. | LS | 1
7.7 | Provision of materials and construction/ installation works in big ablution units (complete setup as per preliminary designs provided including partitions sanitary, boilers and other elements. Note: Sewerage and water network piping installation is included under plumbing BOQ up to each required connection. Price per ablution unit. | EA | 2
7.8 | Provide materials/manufacture and install entry stairs with cover and ground floor emergency exit stair as required from the ground level. See technical Specificatons for details. | LS | 1
7.9 | Provide and Install AC Unit Inverter of 12000 BTU - Refer to technical Specifications for details. | EA | 7
7.1 | Provide and Install AC Unit Inverter of 9000 BTU - Refer to technical Specifications for details | EA | 11
Total #07
8 | Description | Unit | Quantity | Unit price | Total
Container Blocks #7 - Storage Block consisting of Sea Containers 20'
8.1 | Provision of materials and preparation of foundation&grounding works for the container block | LS | 1
8.2 | Positioning of Sea Containers of the prepare foundation as per layout. Note: 7 Second Hand Sea Containers will be provided by EULEX. | LS | 1
8.3 | Provision of materials and execution of works for block roof cover as per technical specifications. | LS | 1
8.4 | Provision of materials and exterior painting of Sea Containers/facade of the block. Prior to painting the surface is thoroughly cleaned painted with primer 1x and 2x with metal oil pain. | LS | 1
Total #08
9 | Description | Unit | Quantity | Unit price | Total
Container Blocks #12 - MSO Block
9.1 | Provision of materials and preparation of foundation&grounding works for the container block | LS | 1
9.2 | Construction Installation works. Positioning of second hand containers (8x )over foundations. Office containers complete will be provided by EULEX. With minor modifications to panel setup that needs to be done to fit to the new layout. See technical specifications for details. | LS | 1
9.3 | Installation of additional office windows 80x120cm for the MSO Office. Containers windows will as well be provided by EULEX. Contractor is to carry the installation and provide prepainted T skirting around the installed windows as per design provided | EA | 4
9.4 | Provide and install PVC ablution unit window dim. 60X80cm including skirting on both sides | EA | 2
9.5 | Provide and install external PVC double wing door.The main entrance door should be of PVC profiles DIM 180/240cm Glass: double, fully insulated, thermal protection, 4/16/4mm. Door is to be equipped with door lock complete, minimum three keys. | EA | 1
9.6 | Provide and install PVC Frame with emergency exit door. With PVC profiles, DIM 180/240cm Glass: double, fully insulated, thermal protection, 4/16/4mm. Emergency door is to be equipped with panic push bar and possibility to close/open with a key from exterior. | EA | 1
9.7 | Provision of materials and construction of flooring and ceiling works in corridor ( structure and all layers) . See technical specifications for details | LS | 1
9.8 | Provision of materials and execution of works for roof cover as per technical specifications. Steel roof trussess (5x) will be provided by EULEX as well. All other materials/accessories for the roof to be provided by contractor. | LS | 1
9.9 | Provision of materials and construction/ installation works in big ablution units (complete setup as per preliminary designs provided including partitions sanitary, boilers and other elements. Note: Sewerage and water network piping installation is included under plumbing BOQ up to each required connection. | LS | 1
9.1 | Provide materials/manufacture and install entry stairs with cover and ground floor emergency exit stair as required. | LS | 1
Total #09
10 | Description | Unit | Quantity | Unit price | Total
Container Blocks #13 - Reception
10.1 | Provision of materials and preparation of foundation & grounding works for the container blocks reception. Price to include also the reinforced slab for postioning of the contractors guard booth beside reception building. Refer to technical specifications for details. | LS | 1
10.2 | Provision of materials and construction/Installation works of containers including floor, walls & ceiling panels complete. Note: Container steel frames only creating the structure of the block all will be provided by EULEX . See technical specifications for all details. (6x) | LS | 1
10.3 | Provision and installation of all doors and windows: Minimum requirements as per preliminary design and security requirements for this specific building are: 4 EA Exterior PVC doors - full panel. 1EA internal PVC office door /half glass panel. 16 EA exterior PVC windows 95x125cm. 3 EA PVC toilet windows 60x80cm. 2 aluminium sliding windows for the reception internal +external. 1EA internal window 95x125 cm and 4 PVC toilet doors 80x205cm | LS | 1
10.4 | Provision of materials and execution of works for block roof cover as per technical specifications. | LS | 1
10.5 | Provision of materials and execution of facade Insulation works as per technical specifications. | LS | 1
10.6 | Provision of materials and installation works in toilet units (complete setup as per preliminary designs provided including partitions sanitary, boilers and other elements. Note: Sewerage and water network piping installation is included under plumbing BOQ up to each required connection. Price per toilet (2f+2m) | EA | 4
10.7 | Provide materials/manufacture and install steel exterior staircase. Refer to technical specifications for details. | LS | 1
10.8 | Provide and Install AC Unit Inverter of 12000 BTU - Refer to technical Specifications for details. | EA | 3
Total #10
11 | Description | Unit | Quantity | Unit price | Total
Container Blocks #14 - Infirmary Block / with new containers and ablution units
11.1 | Provision of materials and preparation of foundation & grounding works for the container block | LS | 1
11.2 | Provision and Installation of new Office Containers of 20' (605x244cm) as per technical specifications provided. Price to include transportation on site. | EA | 8
11.3 | Provision and Installation of new Ablution Units of 10' (244x254cm) as per technical specifications provided and preliminary setup desings, complete with sanitary installatons and accessories. Price to include transportation on site. | EA | 2
11.4 | Provision of materials and construction of flooring and ceiling works in corridors (structure and all layers) . | LS | 1
11.5 | Provision and Installation of aluminium sliding door for emergency room with clear opening of 115cm. Price to include dismantling of container panels/preparation of position for installation of the new door | EA | 1
11.6 | Provision and installation of 1x PVC main entry door, 1x emergency entry door, 1x emergency exit door complete with panels to close the sides, refer to preliminary building designs and technical specifications for more details. | LS | 1
11.7 | Provide materials/manufacture and install entry stairs with cover and ground floor emergency exit stair as required from the ground level. See technical specificatons for details. | LS | 1
11.8 | Provision of materials and construction of emergency entry ramp. Refer to technical specifications for details. | LS | 1
11.9 | Provide and Install AC Unit Inverter of 12000 BTU - Refer to technical specifications for details. | EA | 4
11.1 | Provide and Install AC Unit Inverter of 9000 BTU - Refer to technical specifications for details | EA | 1
Total #11
12 | Description | Unit | Quantity | Unit price | Total
Container Blocks #15 - Reserve Block
12.1 | Provision of materials and preparation of foundation & grounding works for the container blocks. Unit Price: | LS | 1
12.2 | Provision of materials and construction/Installation works of containers including floor, walls & ceiling panels complete. Note: Container steel frames only creating the structure of the block will be provided by EULEX for all three blocks . See technical specifications for all details. | LS | 1
12.3 | Provision of materials and construction of flooring and ceiling works (structure and all layers) in corridors including internal and external staircases. | LS | 1
12.4 | Provision of materials and installation of all doors and windows for the block. | LS | 1
12.5 | Provision of materials and execution of works for block roof cover complete as per technical specifications. | LS | 1
12.6 | Provision of materials and execution of facade Insulation works as per technical specifications. | LS | 1
12.7 | Provision of materials and construction/ installation works in ablution units ,complete setup as per preliminary designs provided including partitions sanitary, boilers and other elements. Note: Sewerage and water network piping installation is included under plumbing BOQ up to each required connection. Price per ablution unit. | EA | 4
12.8 | Provide materials/manufacture and install entry stairs with cover and ground floor emergency exit stair as required from the ground level. See technical Specificatons for details. | LS | 1
12.9 | Provide and Install AC Unit Inverter of 12000 BTU. Refer to technical specifications for details | EA | 18
12.1 | Provide and Install AC Unit Inverter of 9000 BTU. Refer to technical Specifications for details | EA | 6
Total #12
13 | Description | Unit | Quantity | Unit price | Total
Container Blocks #17 - Cleaning contractor block and ablution for external contractor
13.1 | Provision of materials and preparation of foundation & grounding works for the container blocks. Concrete blocks 30x30x15cm are to be used for this specific block to place the containers over as a base. Price to include ablution unit for the FS as per dwg provided. | LS | 1
13.2 | Provision of materials and construction/Installation works of containers including floor, walls & ceiling panels complete. Note: Containers steel frames only creating the structure of the block all will be provided by EULEX . See technical specifications for all details. Including small ablution on the exterior of the building | LS | 1
13.3 | Provision of materials and construction of flooring and ceiling works in corridors ( structures and all layers). | LS | 1
13.4 | Provision of materials and installation of all doors and windows, including the small ablution on the exterior . | LS | 1
13.5 | Provision of materials and execution of works for block roof cover as per technical specifications. | LS | 1
13.6 | Provision of materials and construction/ installation works in ablution units (complete setup as per preliminary designs provided including partitions sanitary, boilers and other elements. Note: Sewerage and water network piping installation is included under plumbing BOQ up to each required connection. Price per ablution unit. | EA | 3
13.7 | Provide materials/manufacture and install entry stairs with cover and ground floor emergency exit stair as required from the ground level. See technical Specificatons for details. | LS | 1
13.8 | Provide and Install AC Unit Inverter of 12000 BTU. Refer to technical specifications for details | EA | 1
13.9 | Provide and Install AC Unit Inverter of 9000 BTU. Refer to technical specifications for details. | EA | 2
Total#13
Note: | EULEX for container blocks construction works will provide and transport on site:
Refurbished containers steel frames only for block 1,2,3,4,5,6, 13,15,17( both size 20' and 10')
Containers complete with panels for MSO Block #12 including roof steel trusses
All Sea Containers for building #7
Infirmary#14: New 20' office containers and 10' ablution units are to be provided by contractor
Buildings installations (electrical, plumbing network, CIS,Heating, fire alarms) are part of each specific discipline/phase breakdowns herewith.

## Cafeteria
Construction New ECM - Design and Build Project
4.2.3 Breakdown - Construction works in Cafeteria
14 | Description | Unit | Quantity | Unit price | Total
Cafeteria
14.1 | Provision of materials and preparation of foundation & grounding works for the complete building. | LS | 1
14.2 | Provision of materials and construction/mounting of the complete steel structure of the building. | LS | 1
14.3 | Provision of materials and installation/construction works for external and internal walls. Refer to technical specifications for wet and dry areas specification of materials and final layers (painting or tiles) | LS | 1
14.4 | Provision of materials and installation/construction floor works - including terrace ( all layers up to final layers as per technical specifications). | LS | 1
14.5 | Provision of materials and installation works for Roof and Ceiling works complete. | LS | 1
14.6 | Provision and Installation of windows and doors for the complete building as indicated in preliminary designs and technical specifications | LS | 1
14.7 | Provision and Installation of (605x2.44cm) Refrigirator split in two chambers with corridor in between as per technical specifications and dwg provided for fruits/vegetables and diary. | EA | 1
14.8 | Provision of materials and construction/ installation works in toilet (complete setup as per preliminary designs provided including partitions sanitary, boilers and other elements. Note: Sewerage and water network piping installation is included under plumbing BOQ up to each required connection. Price per ablution unit. | LS | 1
14.9 | Provision of materials and Installation works for Pergola Terrace Cover and metal fencing | LS | 1
14.1 | Provide and Install AC Unit Inverter of 18000 BTU. Refer to technical specifications for details. | EA | 3
Total 14
Note: | EULEX for this part of works will provide:
Containerised freezer of 20' (605x244 cm)
Buildings installations (electrical, plumbing network, CIS,Heating, fire alarms) are part of specific discipline/phase breakdowns

## Kitchen appliances
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - Provision and Installation of kitchen appliances in Cafeteria
Line item
| Item description |  | Technical Specifications | Quantity | Unit Price | Total | Additional connections
15.1 | Provide and Install BOILING PAN |  | Capacity: 80–120 liters Type: Electric, tilting Power: 12–18 kW, 400V, 3-phase Material: AISI 304 stainless steel body, AISI 316 cooking surface preferred Thermostat range: 50–300°C Manual or motorized tilting Safety thermostat + pressure relief Use: soups, sauces, rice, stews (large batch cooking) Dimensions: 80x92x90cm | 1 |  |  | water supply and sewage connections
15.2 | Provide and Install COOKER 4 hot plates with static oven |  | 1. Cooking Top 4 × heavy-duty cast iron hot plates Power per plate: 2.5 kW (minimum) Total cooktop power: 10 kW Independent thermostatic control per plate Overheat safety protection Spill containment edge around top 2. Oven (Integrated Underneath) Type: Static electric oven (optional fan-assisted preferred) Capacity: Minimum 3–4 GN 1/1 trays Temperature range: 60°C – 300°C Thermostatic temperature control Bottom + top heating elements Oven power: 5–6 kW minimum Interior: Stainless steel or heavy-duty enamel Double-glass insulated oven door Interior light Total power: 15–16 kW approx. Voltage: 400V, 3-phase, 50/60 Hz Full AISI 304 stainless steel body Dimensions: 80x92x90cm | 1
15.3 | Provide and Install COOKER/GRILL (flat top griddle) with stand |  | Cooking surface: 600–900 mm width Power: 6–12 kW electric Plate thickness: 12–20 mm mild steel Thermostat controlled zones Grease collection drawer Dimension: 80x92x90 cm | 1
15.4 | Provide and Install DISHWASHER ( Commercial Hood Type) |  | Type: Hood / pass-through dishwasher Capacity: 60–80 racks/hour Tank capacity: 20–30 L Boiler power: 6–9 kW Wash pump: 0.5–1 kW 400V, 3-phase Water consumption: 2–3 L per cycle Built-in rinse aid & detergent pump | 2 |  |  | water supply and sewage connections required
15.5 | Provide DOUGH MACHINE (Spiral mixer) |  | Bowl capacity: 25–40 kg dough Flour capacity: 15–25 kg Motor power: 2–4 kW 2-speed motor Stainless steel bowl & spiral 380V, 3-phase Safety guard with interlock | 1
15.6 | Provide and Install FOOD DISPLAY Refrigerated salad display counter |  | Length: 1500–2000 mm Temperature: 2–8°C Static or ventilated cooling GN pan compatible Digital thermostat Dimensions: 174x70x130 cm | 1 |  |  | water supply and sewage connections required
15.7 | Provide and Install FOOD DISPLAY Hot food display counter |  | Length: 1500–2000 mm Temperature: 60–90°C Bain-marie wet or dry heating GN pan compatible Power: 2–4 kW Dimensions: 172x70x130 cm | 1 |  |  | water supply and sewage connections required
15.8 | Provide FRIDGE - large commercial |  | Type: Upright double door Capacity: 1000–1400 liters Temperature: 0 to +5°C Stainless steel interior/exterior 220V Fan-assisted cooling Dimensions:140x81x205 cm | 1
15.9 | Provide and Install ELECTRIC DEEP FAT FRYER |  | Capacity: 2 × 15–20 liters Power: 12–18 kW 400V, 3-phase Oil drain valve Safety thermostat Dimensions: 40x92x90 cm | 1
15.1 | Provide MINCER |  | Output: 40-80 kg/hr Power: 1.1–1.5 kW Stainless steel housing Reverse function | 1
15.11 | Provide and Install OVEN Free standing (combi oven) |  | Capacity: 6–10 GN 1/1 trays Power: 12–18 kW Steam + convection Digital programmable control 400V, 3-phase Dimensions: 86x88x93 cm | 1 |  |  | water supply and sewage connections
15.12 | Provide and Install PIZZA OVEN (with stand) |  | Capacity: 6–9 pizzas (30cm) Temperature: up to 400°C Power: 8–12 kW Double deck recommended Dimensions: 72x72x14 cm | 1
15.13 | Provide and Install PASTA COOKER |  | Capacity: 20–30 liters Baskets: 3–6 Power: 6–12 kW Drain valve included Dimensions:40x92x90 cm | 1 |  |  | water supply and sewage connections
15.14 | Provide and Install SINK Double Stainless Steel Sink |  | Size: 1200–1800 mm length Bowl depth: 300 mm With backsplash Drainboard optional AISI 304 stainless steel Dimentions: 150x70x85 cm | 2 |  |  | water supply and sewage connections
15.15 | Provide SLICER |  | Blade diameter: 300 mm or more Power: 250–450W Adjustable slice thickness: 0–15 mm Aluminum body Safety guard | 1
15.16 | Provide CATERING PREPARATION TABLE Dimensions: 150 × 70 × 85 cm |  | Open stainless steel work table with one shelf, wall-supported. Dimentions: 150 × 70 × 85 cm Stainless steel work table designed for professional kitchen use. Constructed from high-quality inox. | 2
15.17 | Provide CATERING PREPARATION TABLE Dimensions: 200 × 70 × 85 cm |  | Open stainless steel work table with one shelf, wall-supported. Dimentions: 200 × 70 × 85 cm Stainless steel work table designed for professional kitchen use. Constructed from high-quality inox. | 2
15.18 | Provide CATERING PREPARATION TABLE Dimensions: 100 × 70 × 85 cm |  | Open stainless steel work table with one shelf, wall-supported. Dimentions: 100 × 70 × 85 cm Stainless steel work table designed for professional kitchen use. Constructed from high-quality inox. | 2
15.19 | Provide CATERING PREPARATION TABLE Dimensions: 190 × 70 × 85 cm |  | Open stainless steel work table with one shelf, wall-supported. Dimentions: 190 × 70 × 85 cm Stainless steel work table designed for professional kitchen use. Constructed from high-quality inox. | 1
15.2 | Provide CATERING PREPARATION TABLE Dimensions: 140 × 70 × 85 cm | #VALUE! | Open stainless steel work table with one shelf, wall-supported. Dimentions: 140 × 70 × 85 cm Stainless steel work table designed for professional kitchen use. Constructed from high-quality inox. | 1
15.21 | Provide and Install SINK Dimensions: 150 x 75 × 85 cm |  | Single stainless steel sink with opeing on the left side Dimentions: 150 x 75 × 85 cm | 1 |  |  | Water supply and sewage connections
15.22 | Provide SHELF Dimensions: 185 × 40× 180 cm |  | Open shelf, 4 shelfs, inox. Dimentions: 185 × 40× 180 cm | 4
15.23 | Provide SHELF Dimentions: 150 × 40 × 180 cm |  | Open shelf, 4 shelfs, inox. Dimentions: 150 × 40 × 180 cm | 2
15.24 | Provide SHELF Dimentions: 200 × 40 ×180 cm |  | Open shelf, 4 shelfs, inox. Dimentions: 200 × 40 ×180 cm | 1
15.25 | Provide SHELF Dimentions: 170 × 40 × 180 cm |  | Open shelf, 4 shelfs, inox. Dimentions: 170 × 40 × 180 cm | 1
15.26 | Provide SHELF Dimentions: 180 × 70 × 85 cm |  | Open shelf, 4 shelfs, inox. Dimentions: 180 × 70 × 85 cm | 1
15.27 | Provide PLATE FOR FOOD DISPLAY Gastronom Standard GN, 1/1-65 |  | For cold food display Gastronom Standard GN, 1/1-65 | 5
15.28 | Provide PLATE FOR FOOD DISPLAY Gastronom Standard GN, 1/1-100 |  | For hot food display Gastronom Standard GN, 1/1-100 | 5
15.29 | Provide TRAY TROLLEY |  | 18 x GN2/1, the space between the shelfs 8 cm Food Service Trolley, Inox | 3
Total #15

## Gym-Train and Rec
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - Gym, Training and Recreation Buildings
16 | Description | Unit | Quantity | Unit price | Total
Gym Building
16.1 | Provision of materials and preparation of foundation & substructure works for the complete building. | LS | 1
16.2 | Provide and install steel structure complete for the building (bolted connections, bracing and structure stability works). | LS | 1
16.3 | Provide and install externall wall calding ( sandwich panels) and roof cover panels (sandwich panels) with all required elements and accesssories (gutters, skirtings, flashings, etc). Complete building envelope. | LS | 1
16.4 | Provide and install all exterior and interior windows & doors for the building. See technical specifications for details . | LS | 1
16.5 | Provide materials and construction complete interior works and fInishes including partitions, floor & ceiling works in changing rooms, corridors and shower/toilets area of the building, complete as per technical specifications. | LS | 1
16.6 | Provide materials and construction complete interior works for both saunas male and female. | LS | 1
16.7 | Provide materials and construction complete interior works and fInishes in the training area, floor layers completed with final layer epoxy. Refer to technical specifications | LS | 1
16.8 | Provide and install all sanitary fixtures (shower units, toilets, urinals, washbasins, boilers etc. | LS | 1
16.9 | Provide material and install main entry cover | LS | 1
Total 16
17 | Description | Unit | Quantity | Unit price | Total
Outdoor GYM and Court
17.1 | Provide and install basketball post complete, including foundation with anchoring. | LS | 1
17.2 | Install the outdoor Gym Seel structure which is to be provided by EULEX. Dwg of the structure is provided as part of specifications. | LS | 1
Total 17
18 | Description | Unit | Quantity | Unit price | Total
Training House
18.1 | Provision of materials and preparation of foundation & substructure works for the complete building. | LS | 1
18.2 | Provide and install steel structure complete for the building (bolted connections, bracing and structure stability works). | LS | 1
18.3 | Provide and install externall wall calding ( sandwich panels) and roof cover panles (sandwich panels) with all required elements and accesssories (gutters, skirtings, flashings, etc). Complete building envelope. | LS | 1
18.4 | Provide materials and construction complete interior works and fInishes including partitions, floor works, etc as per technical specifications | LS | 1
18.5 | Provide and install all exterior and interior windows & doors for the building. See technical specifications for details. | LS | 1
18.6 | Provide material and install main entry steel cover | LS | 1
Total 18
19 | Description | Unit | Quantity | Unit price | Total
Recreation Building
19.1 | Provision of materials and preparation of foundation & substructure works for the complete building. | LS | 1
19.2 | Provide and install steel structure complete for the building (bolted connections, bracing and structure stability works). | LS | 1
19.3 | Provision of materials and installation/construction works for external and internal walls. Refer to technical specifications for wet and dry areas specification of materials and final layers (painting or tiles) | LS | 1
19.4 | Provision of materials and installation/construction floor works (all layers). | LS | 1
19.5 | Provide and install all exterior and interior windows & doors. See technical specifications for details . | LS | 1
19.6 | Provision of materials and installation works for Roof and Ceiling works complete. | LS | 1
19.7 | Provide and install all sanitary fixtures (toilets, washbasins, boilers etc) | LS | 1
19.8 | Provide material and install stairs and cover for both main entry and exit to barbeque area. | LS | 1
19.9 | Provide and Install AC Unit Inverter of 18000 BTU. Refer to technical specifications for details. | EA | 1
Total 19
Note: | Steel structure for outdoor training will be provided by EULEX, as per provided designs, the same are to be installed by contractor
All exterior works: barbeque area and outdoor gym and court ground works are included under Horizontal Services works breakdown #02
Buildings installations (electrical, plumbing network, CIS,Heating, fire alarms) are part of specific discipline/phase breakdowns.

## MSD
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - Modification and refurbishment of MSD Building (existing building)
20 | Description | Unit | Quantity | Unit price | Total
MSD Building ( BMU, Logistics and Transport Stores and workshops )
20.1 | Demolishing of raised platforms/stairs and removal of debris from site with transportation to a designated dump site. Height of platforms 1m /1.2m. Supporting walls are made of concrete blocks while the slab with hollow clay blocks. Refer to technical specifications and drawings for more details. Estimated qty: 330m2 | LS | 1
20.2 | Demolishing of concrete staircase at the back administrative offices and removal of debris from site. | LS | 1
20.3 | Dismantling of corridor door to the admin offices 90x205cm | EA | 1
20.4 | Dismantling of emergency door 90x205cm | EA | 1
20.5 | Dismantling of aluminium main entry door to the building dim 265x297cm | EA | 1
20.6 | Dismantling of front facade windows dim 500x248cm | EA | 2
20.7 | Dismantling of side facade ( north and south) windows dim 200x126cm | EA | 5
20.8 | Dismanling of electrical installations and panel | LS | 1
20.9 | Dismantling of toilets PVC partitions, sanitary and tiles and removal of debris from site. All four | LS | 1
20.1 | Dismantling of toilet windows 60x60cm | EA | 2
20.11 | Dismantling of main toilet doors 80x205cm | EA | 2
20.12 | Dismantling of gypsum partition at the entrance and removal of debris from site . Estimated qty: 29m2 | LS | 1
20.13 | Create openings for new doors, windows and rolling doors as per new building designs by cuting/ demolishing the facade wall made of concrete blocks/insulation. Removal of debris from site and transportation to an authorised dump site. Estimated qty from preliminary designs: 50m2 | LS | 1
20.14 | Provide material and create supporting reinfoced concrete lintels over the new 3 rolling doors to be installed, Emergency door 1x, reception doors 2x, to support the masonary above. | LS | 1
20.15 | Provide material and lay concrete blocks on the facade wall to close the gaps after dismantling of windows or creating the new openings. Price to include, facade insulation and repair works around the new created openings for the installation of new doors/windows from both sides. | LS | 1
20.16 | Provision of materials and repair of flooring on positions where the platform and staircase has been demolished. Preparing the surface to receive the final layer. | LS | 1
20.17 | Provide material, and laying of epoxy flooring. Prepare and clean the flooring, laying of primer epoxy paint and epoxy resin in Transport, Logistics and BMU areas. Estimated qty prom peliminary designs: 580m2 | LS | 1
20.18 | Provide material and install 5cm sandwich wall panels over steel supporting structure (rectangular profiles 60x40x3mm) , dividing the building as per new layout creating separate zones between MSD components and also storage areas. Price to include panels and supporting structure. Lowest heigh of the building is 6 m ( trusses level) , highest point is 8m in the middle. Estimated qty from preliminary designs: 551m2 | LS | 1
20.19 | Provide material and construct gypsum wall partitions for the offices in Transport workshop/Logistics as per the new setup. Internal partition wall type W112, comprising of metal stud framework with gypsum plasterboards on both sides of 2x12.5mm and mineral wool insulation in between, including reinforced framing to door openings and windows. Estimated qty from preliminary designs: 97m2 | LS | 1
20.2 | Provide and install ceiling with layers aluminum CW profiles 100mm every 50cm, mineral wool d=100mm covered with plastic sheet d=0.2mm and plasterboard from inside plywood from above. Estimated qty from preliminary designs: 32m2 | LS | 1
20.21 | Provide and install ceiling with layers aluminum CW profiles 100mm every 50cm, mineral wool d=100mm covered with plastic sheet d=0.2mm and thin plywood d=0.5mm. Estimate qty from preliminary designs: 46m2 | LS | 1
20.22 | Provide and install mineral fiber suspended ceiling panels dim 60x60 cm, complete with all the necessary fixtures/supporters for the new offices on the 1st floor. Sample to be provided for approval prior to installation, Estimated quantity from preliminry designs: 46m2 | LS | 1
20.23 | Provide and install two emergency doors with panic push bars. Refer to technical specifications for details | EA | 2
20.24 | Provide and install PVC doors dim 90x205cm to the toilets loby. | EA | 2
20.25 | Provide material and install PVC doors for toilet cabins dim 80x205cm | EA | 2
20.26 | Provide and install exterior aluminium doors for Transport and Logistics Reception rooms and BMU 90x205cm | EA | 3
20.27 | Provide and install interior aluminium doors for offices 90x205cm | EA | 6
20.28 | Provide material manufacture and install steel staircase for Transport workshop. Refer to technical specifications for details | EA | 1
20.29 | Provide and install rolling door dim 400x400+60cm. Refer to technical specifications for details | EA | 2
20.3 | Provide and install rolling door dim 320x400+60cm. Refer to technical specifications for details | EA | 1
20.31 | Provide and install Aluminium BMU Store double wing door dim 140x210cm | EA | 1
20.32 | Provide and Install double wing aluminium door for Transport Store door 160x210cm | EA | 1
20.33 | Provide and install PVC windows exterior, tilt and turn opening, color/material to match to other facade windows of the building dim, 120x140cm | EA | 2
20.34 | Provide and install PVC windows exterior, tilt and turn, color/material to match to other existing windows of the building dim, 200x126cm | EA | 2
20.35 | Provide and install aluminium interior windows for ground floor offices dim 220x100cm | EA | 2
20.36 | Provide material and repair the walls after demolishing works of the platform and stairs where and as required and prepare it for painting | LS | 1
20.37 | Provide with material and paint the interior of perimeter walls (upper part with base paint & final dispersive paint reaching a uniform color. Color of paint will be assigned by supervisor. Estimated qty from preliminary designs 860m2 | LS | 1
20.38 | Provide with material and paint the interior of perimeter walls (down part in h=140cm) with base paint & final oil paint light grey color. Estimated qty from preliminary designs: 130m2 | LS | 1
20.39 | Provision of materials and plastering the walls for Transport and Logistics Office. Estimated qty from preliminary designs: 75m2 | LS | 1
20.4 | Provision of materials and applying self leveling compound. Estimated qty from preliminary designs : 57m2 | LS | 1
20.41 | Provision of materials and installation of laminate flooring Estimated qty from preliminary designs: 81.60m2 | LS | 1
20.42 | Provision of materials and construction of syporex partitions in toilets as per dwg provided . Estimated qty from preliminary designs: 14m2 | LS | 1
20.43 | Povision of materials and installation of floor screed. Estimated qty from preliminary designs: 50m2 | LS | 1
20.44 | Provision of materials and laying of hydroinsulation in toilets/shower. Estimated qty from preliminary designs: 41m2 | LS | 1
20.45 | Provision of materials and installation of floor tiles in toilets. Estimated qty from preliminary designs: 24m2 | LS | 1
20.46 | Provision of materials and installation of wall tiles in toilets. Estimated qty from preliminary designs: 104m2 | LS | 1
20.47 | Provision of materials and interior painting works - 1st floor offices . Estimated qty from preliminary designs: 160m2 | LS | 1
20.48 | Provide and install toilet seats, including water flush cistern and built in biddet | EA | 2
20.49 | Provide and install urinal set | EA | 2
20.5 | Provide and install shower head and flexible hose (wall hanged as well), water tap and shower drainage. | EA | 2
20.51 | Provide and install washbasin with water tap complete | EA | 2
20.52 | Provide and install boiler 80ltr | EA | 2
20.53 | Provide and install wall mirror min 60x80cm | EA | 2
20.54 | Provide material and construct concrete ramps in front of rolling doors, width of the doors (3x) | LS | 1
20.55 | Dismantling of vehicle lifts (2 post electro hydraulic lift, capacity 4000kg) from the existing w/sh located in Mitrovica, transporting it to the new location and installing it in the new position - Distance between two locations average 4km. See technical specs. | EA | 2
20.56 | Dismantling of vehicle lift (4 post electro hydraulic lift, capacity 8000kg) from the existing w/sh located in old Transport w/sh, trasporting it to the new location and installing it on site - Distance between two locations average 4km. See technical specs | EA | 1
20.57 | Provision of materials and installation of compressor steel piping all around transport workshop with connection points to lifts and other equipments as required. Price to include all required accessories for a functional line - 10 bar pressure. Compressor is to be positioned on site by EULEX and indicated in the floor plan from where the contractor is to enter through fasade on the interior with pipes fixed on the walls and reach each equipment requiring the connection. | LS | 1
20.58 | Design and Build works Vehicle Exhaust Extraction system - Fans with automatic hose reel for the ascent and the descent of the flexible hose, with control box for stop of the hose or switch up / down and all other necessary accessories, canal of galvanized metal sheet and ventilation grills. In the price to be foreseen 2EA Exhaust Extraction Units. | EA | 2
20.59 | Provide material and repaint facade of the building. Primer 1x, facade paint 2 x as per technical specifications. Color to be chosen by EULEX Representative. Estimated qty from preliminary designs: 730m2 | LS | 1
Offices Section within the MSD Building
20.6 | Create openings for new doors, windows as per new building designs by cuting/ demolishing the facade wall made of concrete blocks/insulation. Removal of debris from site and transportation to an authorised dump site. th=20cm. Estimated qty from preliminary designs: 12m2 | LS | 1
20.61 | Provide material and create supporting reinfoced concrete lintels over the new windows and door | LS | 1
20.62 | Supply,manufacture, installation, anchoring, finishing, a complete mid‑floor system for first‑floor offices including all structural elements, sub‑layers, finishes, fixings, and connections to the existing reinforced concrete building structure. Using the 6 meter floor/trusses distance to create a two story offices. Price to include also a supporting structure for suspended ceiling of the 1st floor. Estimated qty from preliminary design: 76m2 | LS | 1
20.63 | Provide materials, manufacture and install interior steel staircase for Administrative part of the building as per technical specifications | LS | 1
20.64 | Provide and install galvanized steel stud framework fixed to sandwich panel via brackets, insulation in between and 1x12.5mm plasterboard on the inside including preparation works making it ready for painting . Estimated qty as per preliminary design: 110m2 | LS | 1
20.65 | Provide material and construct internal partitions as per new setup. Internal partition wall type W112, comprising of metal stud framework with standard plasterboards on both sides of 2x12.5mm and mineral wool insulation in between, including reinforced framing to door openings. Estimated qty from preliminary design 82m2 | LS | 1
20.66 | Provide material and construct internal partitions as per new setup. Internal partition wall type W112, comprising of metal stud framework with moisture-resistant plasterboards on both sides of 2x12.5mm and mineral wool insulation in between, including reinforced framing to door openings. Estimated qty from preliminary design: 29.60m2 | LS | 1
20.67 | Provide material and paint interior of the new build offices . Estimated qty from preliminary design: 340m2 | LS | 1
20.68 | Provide and install mineral fiber suspended ceiling panels dim 60x60 cm, complete with all the necessary fittings.Estimated qty from preliminary designs: 138m2 | LS | 1
20.69 | Provide and install suspended ceiling panels dim 60x60 cm, complete with all the necessary fittings suitable for wet areas. Estimated qty from preliminary designs: 13m2 | LS | 1
20.7 | Provide and install laminate flooring as final layer. Estimated qty from preliminary designs: 138m2 | LS | 1
20.71 | Provide material and install floor tiles for toilets and kitchenette. Estimated qty from preliminary designs: 12.81m2 | LS | 1
20.72 | Provide material and install wall tiles for toilets and kitchenette. Estimated qty from preliminary designs: 51m2 | LS | 1
20.73 | Provide and install PVC windows exterior, tilt and turn, color/material to match to other existing windows of the building dim, 200x126cm | EA | 4
20.74 | Provide and install PVC window exterior, tilt and turn, color/material to match to other existing windows of the building dim 60x80cm | EA | 2
20.75 | Provide and Install wooden office doors 90x205cm | EA | 5
20.76 | Provide and install toilet PVC doors 80x205cm | EA | 1
20.77 | Provide and install toilet PVC doors 70x205cm | EA | 2
20.78 | Provide and install Aluminium main entry doors 200x250cm | EA | 2
20.79 | Provide and install washbasin with water tap complete | EA | 2
20.8 | Provide and install toilet seats, including water flush cistern and built in biddet | EA | 2
20.81 | Provide and install boiler low mounted 10ltr | EA | 2
20.82 | Provide and install wall hung mirror 60x40cm | EA | 2
20.82 | Installation of split AC Units of 12000BTU - to be provided by EULEX - Office space only | EA | 10
Total 20
21 | Description | Unit | Quantity | Unit price | Total
Vehicle Inspection Pit - for "RILA" armoured ambulace vehicles
21.1 | Design and Build - Vehicle Inspection Pit outdoor, covered with steel roof, as per preliminary designs and techncial specifications. | LS | 1
Total 21

## Electrical
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - Electrical Installations
22 | Description | Unit | Quantity | Unit price | Total
External Electrical Installations
22.1 | Provide material and install external underground power distribution network cabling from transformer/substation to each building /facility/service/site/plant/datacenter/heating station, parade yard etc. All cabling to be placed in ducting pipes when underground and in overground positions covered with trunking. Price to include Compound Main Electrical Panels, cabling, grounding, and any required fittings& installations to make the network functional. Trenches and underground ducting/conduits are to be included in BOQ 02 - infrastructure seperately from this position. | LS | 1
22.2 | Provide material and install external streel lights LED 50w, lights to be installed on galvanised steel poles fixed on corner of the buildings. Indicative positions of lights can be found in preliminary design of external electrical installations. Refer to technical specifications for details. Price is to include cabling to the nearest panel, dark sensor and any other fitting as required. | EA | 44
22.3 | Provide material and install illumination for the central part of the Compound ( green area and parking) by use of various decorative/lights LED creating a uniform illumination during night time for pedestrians. | LS | 1
22.4 | Provide material and install external LED spot lights around the perimeter of the helipad/fixed on T walls, final number to be determinded with calculations and design of electrical engineer. | LS | 1
22.5 | Provide material and install external LED lights for the Outdoor Basketball Half Court and Grand Parades area illumination fixed on galvanised poles , minimum height 5m | EA | 6
Internal Electrical Installations including emergency/exit lights
22.5 | Provide materials and install internal electrical installations complete in Block #01 Platoon Block. Refer to technical specifications point 4.4 for detailed requirements. | LS | 1
22.6 | Provide materials and install internal electrical installations in Block #02 Platoon Block . Refer to technical specifications point 4.4 for detailed requirements. | LS | 1
22.7 | Provide materials and install internal electrical installations in Block #03 Platoon Block. Refer to technical specifications point 4.4 for detailed requirements. | LS | 1
22.8 | Provide materials and install internal electrical installations in Block #04 Female Block. Refer to technical specifications point 4.4 for detailed requirements. | LS | 1
22.9 | Provide materials and install internal electrical installations in Block #05 Commander Block. Refer to technical specifications point 4.4 for detailed requirements. | LS | 1
22.1 | Provide materials and install internal electrical installations in Block #06 Office Block. Refer to technical specifications point 4.4 for detailed requirements. | LS | 1
22.11 | Provide materials and install internal electrical installations in Block #07 FPU Storage. Refer to technical specifications point 4.4 for detailed requirements. Minimal installations (lights and 1 socket per container) | LS | 1
22.12 | Provide materials and install internal electrical installations in Building #08 Recreation Building. Refer to technical specifications point 4.4 for detailed requirements. | LS | 1
22.13 | Provide materials and install internal electrical installations in Building#09 Training House. Refer to technical specifications point 4.4 for detailed requirements. | LS | 1
22.14 | Provide materials and install internal electrical installations in Building #10 Gym bld. Refer to technical specifications point 4.4 for detailed requirements. | LS | 1
22.15 | Provide materials and install internal electrical installations in Building #11 Cafeteria. Refer to technical specifications point 4.4 for detailed requirements. | LS | 1
22.16 | Provide materials and install internal electrical installations in Block 12 MSO Block. Refer to technical specifications point 4.4 for detailed requirements. Note that containers will be equipped with sockets, switches, lights. Panel will be provided for this block only. The rest is to be included in the price (corridor, toilet, other not listed) | LS | 1
22.17 | Provide materials and install internal electrical installations in Block 13 Reception. Refer to technical Specifications point 4.4 for detailed requirements. | LS | 1
22.18 | Provide materials and install internal electrical installations in Block 14 Infirmary. Refer to technical Specifications point 4.4 for detailed requirements. Container for this block will be new with electrical installation included which is to be taken into consideration during calculations for the building and not included in the price. | LS | 1
22.19 | Provide materials and install internal electrical installations in Block 15 Reserve Block. Refer to technical Specifications point 4.4 for detailed requirements. | LS | 1
22.2 | Provide materials and install internal electrical installations in Building 16 MSD Building. Refer to technical Specifications point 4.4 for detailed requirements. | LS | 1
22.21 | Provide materials and install internal electrical installations in Building #17 Cleaning Contractor. Refer to technical Specifications point 4.4 for detailed requirements. | LS | 1
22.22 | Provide materials and install internal electrical installations in Armory #19. Refer to technical Specifications point 4.4 for detailed requirements. | LS | 1
Backup system - Generators
22.23 | Installation/Connection of backup system 2x generators for the Compound with ATS and fuel tank. Generators of 800kva with ATS and fuel tank will be provided and transported on site by EULEX. All other materials, works and fittings required for a functional back up system in the Compound are to be provided by contractor | LS | 1
Other
22.24 | Provide material and install electrical installation for the Fuel Station setup #18, LED lights installed on T walls for illumination of the area, feeding for the equipments and cabin. As preliminary solution the connection would be from building #17 panel | LS | 1
22.25 | Provide material and install electrical installation for the vehicle inspection pit and the cover. As preliminary solution the connection would be from building #16 panel | LS | 1
22.26 | Provide material and install LED lights for the vehicle entrance shed and illumination of pedestrian entry. | LS | 1
22.27 | Provide material and install electrial installations on the covered parking spots ( lights and charging point for the vehicles) A,B,C | LS | 1
22.28 | Provide material and install electrical connection for Datacenter Container /3ph | LS | 1
Total 22
Note: Ground work for trenches are to be included under breakdown, Infrastructure - 2.1
Ducting pipes are also to be included under reakdown, Infrastructure - point 2.1
Power supply is to be provided to each equipment/installation foreseen with the final designs - heating plants, filtering system, security equipment, etc
for a functional operation of the Compound which is to be counted with their installation price

## CIS
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - CIS Installations
23 | Description | Unit | Quantity | Unit price | Total price
Outdoor Fiber Optic Backbone Cabling System
23.1 | Complete Outdoor Fiber Optic Backbone Cabling System (OM4, 12 core, ring topology), including supply, installation, splicing, termination, testing, documentation, and commissioning – all as per tender specifications provided. | LS | 1
Indoor Horizontal strucutred Cabling (UTP)
23.2 | Single Connection (all‑inclusive) , as per tender specifications provided. Minimum requirements: - Category 6 UTP cable - Cable containment (PVC conduit, trunking, accessories) - Dual RJ45 Cat6 outlet including keystones, faceplate, and back box - Patch panel port and termination - Cable management within cabinet - Termination, labeling, and identification at both ends - Testing and certification - Documentation and as‑built records - Labor, tools, consumables, and waste disposal | EA | 1029
CCTV Inner Network Infrastructure
23.3 | • Provision and installation of: - Cable management solutions - CAT6 UTP cabling - Cable containment systems (PVC conduits and/or cable trays) - Dual-sided RJ45 terminations - Termination, labeling, testing, certification, and full documentation of all installed cabling. See technical specifications for more details. | EA | 16
Camera Poles
23.4 | Provide and install metal poles approximate length 3m, mounted on the highest points of following buildings: Block #01, Reserve Block #15, Cafeteria#11, Gym #10, MSD Building #16 | EA | 5
23.5 | Provide and install metal poles 4m overground level, dim 100x100x3mm, price to include fundation/welding works as required , painting with primer paint and oil pain 2 x ( main entrance) | EA | 3
23.6 | Provide and install metal poles approx, 1 m mounted on the front building facade / Reception | EA | 2
23.7 | Provide and install metal poles mounted on T walls and cover structure (Helipad 2x, Ammunition Depo 2x, fuel station 2x) , approx 1m' | EA | 6
Total 23
Note: | Trenches ground works are to be included under infrastructure including ducting
Containerised Data Center will be provided by EULEX
Network cabinets to be provided by EULEX.
All Cameras (PTZ and Dome) will be provided and installed by EULEX, contractor is to establish the required infrastructure as per specifications for such installation to take place.

## Mechanical
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - Mechanical Installations
24 | Description | Unit | Quantity | Unit price | Total
Heating Station #01 - electricity
24.1 | Provide and Install Heating Station complete #01 - Central Heat Pump | LS | 1
24.2 | Provide and Install preinsulated underground heating pipes from the station #01 to each building with all required fittings and accessories. Price to include also trenches ground works and boxing at entry of each building. | LS | 1
24.3 | Provide materials and install internal Heating System with radiators for Block 01 - Platoon Block | LS | 1
24.4 | Provide materials and install internal Heating System with radiators for Block 02 - Platoon Block | LS | 1
24.5 | Provide materials and install internal Heating System with radiators for Block 03 -Platoon Block | LS | 1
24.6 | Provide materials and install internal Heating System with radiators for Block 04 - Female Block | LS | 1
24.7 | Provide materials and install internal Heating System with radiators for Block 05 - Commander Block | LS | 1
24.8 | Provide materials and install internal Heating System with radiators for Block 06 - Office Block | LS | 1
24.9 | Provide materials and install internal Heating System with radiators for Block 08 - Recreation Building | LS | 1
24.1 | Provide materials and install internal Heating System with radiators for offices and and Calorifers store and workshops for Building 16 - MSD | LS | 1
Heating Station #02
24.11 | Provide and Install Heating Station complete #02 - Central Heat Pump Station | LS | 1
24.12 | Provide and Install preinsulated underground heating pipes from the station #02 to each building with all required fittings and accessories. Price to include also trenches ground works and boxing at entry of each building. | LS | 1
24.13 | Provide material and install internal Heating System with calorifers for Traning Building #09 | LS | 1
24.14 | Provide material and install internal Heating system with radiators for the changing rooms and calorifers for training ares in Gym Building #10 | LS | 1
24.15 | Provide materials and install internal Heating System with radiators for Block 11 - Cafeteria | LS | 1
24.16 | Provide materials and install internal Heating System with radiators for Block 12 -MSO Block | LS | 1
24.17 | Provide materials and install internal Heating System with radiators for Block 13 - Reception | LS | 1
24.18 | Provide materials and install internal Heating System with radiators for Block 14 - Infirmary | LS | 1
24.19 | Provide materials and install internal Heating System with radiators for Block 15 - Reserve Block | LS | 1
HVAC for other Buildings
24.2 | Provision and Installation of Ventilation System for Dining room in Cafeteria Building #11 | LS | 1
24.21 | Provision and Installation of Exhaust Hud/ventilation for kitchen in Cafeteria | LS | 1
24.22 | Provision and Installation of Ventilators in MSD workshops/stores | LS | 1
Total 24
Note: | 2 Sea Container will be provided by EULEX for Heat Pump Stations setup if required
Design cost for all above components to be included in the design phase/mechanical
Refer to Technical Specifications and provisional designs for more details

## Plumbing
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - Plumbing Installations
25 | Description | Unit | Quantity | Unit price | Total
Main Water Supply Network - Outdoor
25.1 | Provision of materials and execution of works for exterior underground water network installations from water meter up to each required connection point ( building or other) . Price to include trenches, manholes as required, PE pipes with all accessories and all components of the exterior network, pump house with backup water tanks. Refer to technical specifications for more details. Pipes to be dimensioned as part of the design phase. Water tanks (6x5000ltr) for the backup system will be provided by EULEX, all other accessories/materials for the works to be provided by contractor. | LS | 1
25.2 | Provision of material and installation of the water filtering system for the Compound at the entry point of the compound. See technical specifications for details. | LS | 1
Main Sewerage System Network - Outdoor
25.3 | Provision of materials and execution of works for sewerage network installations from each building/premises or other that require sewerage connection until treatment plant. Price to include trenches ground works, manholes, septic tank and pump (depending on the design) and all components of the network. Refer to technical details for more details. | LS | 1
25.4 | Provision and Installation of Containerised Treatment Plant complete ( max capacity 200 users) as per technical specifications with connection to the nearby manhole for discharge/ final discharge to Sitnica River after treatment. See technical specifications for all details. | LS | 1
25.5 | Provision and installation of grease seperator / interceptor for restaurant/kitchen. | EA | 1
Indoor Water/Sewerage Network Installations in buildings and other premises
25.6 | Provision of materials and execution of works for complete internal water and sewerage network for Block 1, 2 and 3 ( 4x big ablution units, dry corner of washing/drying machines, etc) . Refer to the dwg provided and specifications for more details. | LS | 3
25.7 | Provision of materials and execution of internal works for complete water and sewerage network for Block 4 (4x small ablution units, laundry corner washing/drying machines, kitchenette sink) | LS | 1
25.8 | Provision of materials and execution of works for complete water and sewerage network for Block 5 ablution units ( 4x per block) and laundry room washing/drying machines, kitchenette sinks | LS | 1
25.9 | Provision of materials and execution of works for complete water and sewerage network for Block# 6 ablution units ( 2x per block) and laundry corner washing/drying machines, kitchenette sink | LS | 1
25.1 | Provision of materials and execution of works for complete water and sewerage network for Building #8 toilets (m/f) and kitchnette | LS | 1
25.11 | Provision of materials and execution of works for complete water and sewerage network for Building #09 changing /shower rooms complete setup. | LS | 1
25.12 | Provision of materials and execution of works for complete water and sewerage network for Building #011 Cateteria ( toilets, kitchen, serving area). | LS | 1
25.13 | Provision of materials and execution of works for complete water and sewerage network for Block 12 ablution units ( 1x per block) and kitchenette sink | LS | 1
25.14 | Provision of materials and execution of works for complete water and sewerage network for Block #13 toilets and kitchenette sink up to connection to the main networks. | LS | 1
25.15 | Provision of materials and execution of works for complete water and sewerage network for Block #14 ablution units (2x small) and washbasins in each room (3x) | LS | 1
25.16 | Provision of materials and execution of works for complete water and sewerage system for Block #15 ablution units (4x big ablution unit) | LS | 1
25.17 | Provision of materials and execution of works for water and sewerage network for existing building #16 ( toilets/kitchenettes/etc). | LS | 1
25.18 | Provision of materials and execution of works for complete water and sewerage network for Block #17 ablution units (3x) and kitchenette sink | LS | 1
25.19 | Other connection points required within the Compound: Connection to the exterior networks (point 25.1) of DataCenter container, Heating plants 2x, fuel station hose connection point and minimum two other hose connection point spread in different angles of the compound | LS | 1
Buildings and Compound Drainage System
25.2 | Provision of materials and execution of works for drainage system for the Compound until the discharge manhole at the lowest point of the Compound ( around buildings,roads,perimeter/ helipad/ and other compound areas) Price to include also trenches ground works, grills/gullies, manholes and all components of the network for a functional system. Refer to technical details for more details. | LS | 1
25.21 | Provision and installation of oil separator for vehicle workshop and inspection pit | EA | 1
Rainwater accumulation system and reuse
25.22 | Provision and installation of underground rainwater accumulation system complete as per technical specifications , 1500-1700m2 covered area. | LS | 1
Total 25
Note: | 6x 5000ltr water tanks are to be provided by EULEX
Designs for all above to be included under Plumbing / Designs Services

## Firefighting
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - Firefighting Systems
26 | Description | Unit | Quantity | Unit price | Total
Fire Alarms system
26.1 | Provision, installation, commissioning and all other necessary parts, works, planning and engineering that may arise to complete installation of fully operational Fire Detection and Alarm System in the new EULEX Compound in Mitrovica. Offered price is to include all actions required. Refer to technical specifications for details. | LS | 1
Total 26
27 | Description | Unit | Quantity | Unit price | Total
External Hydrants
27.1 | Provision and Installation of the Outdoor Fire Hydrants Network for the Compound including all required ground works/trenches, installations/equipment for an operational external firefighting system. Refer to Technical Specifications point 4.9 Minimum system requirements work: - Survey of the area/marking of pipeline. - Excavation of trenches/backfilling - Provision of installation of the pipeline. - Provision and installation of the above ground Fire Hydrants with all the required accessories for a functional system. - Provision and Installation of Fire Hydrants cabinets complete with all the required equipment/accessories. - Connection of the new installed network to the city line. - Testing of the network. | LS | 1
Total 27

## SOLAR PANELS
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - Renewable Energy / Solar Panels system
28 | Description | Unit | Quantity | Unit price | Total
Solar Panel System
28.1 | Provision of materials and installation of Solar panels system complete - 260kWp capacity (+-3%) - Solar system: with zero export device, no energy is fed into the grid. Price to include complete set ( solar panels, inverter, DC cable with DC connectors, AC Cables, AC protection devices, communcation LAN cable, etc) . System is to have online monitoring. Design to be priced/included in Designs BOQ Refer to Technical Specifications 4.10 for more details | LS | 1
Total 28

## FS &Other
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - Fuel Station
29 | Description | Unit | Quantity | Unit price | Total
Fuel Station
29.1 | Provide material and construct reinforced concrete base for positioning of 30 000 ltr fuel tank. Concrete to be extended for fuel pump and RFID post on the same level, raised over asphalt level ~ 20cm. Estimated m2: 55. See technical specifications for details. | LS | 1
29.2 | Provision of materials and installation of curbstones around the concreted area dim 24/18-12cm. Estimated quantities: 35m' | LS | 1
29.3 | Provision of ducting pipes 2x Ø75mm under the concrete slab from fuel tank outlet to the fuel pump and from RFID post to the fuel pump | LS | 1
29.4 | Installation of cabin dim 244x254cm over concrete blocks 30x30x15cm. Cabin will be provided by EULEX | EA | 1
29.5 | Provision of materials and installation of entry stairs to the cabin. Estimated two height of max 17cm, width of stair 100cm. Steel structure with aluminium ribbed sheets. | EA | 1
29.6 | Cutting of asphalt, excavation, provision of materials and construction of green area at the back of fuel tank. Estimated m2 from provisional layout 57.5m2/perimeter 47.5m'. Note: The surface is currently asphalted. Debris to be forseen to be removed from site and soil included for the green area. Curb stones 24/18-12cm | LS | 1
29.7 | Provide materials, construct, install, a complete linear grilled drainage for the fuel station area, including an oil separator, complete and fully operational. The system shall be designed to collect surface runoff and fuel spillage, channel it through a properly sized oil separator, and subsequently discharge treated effluent into the new drainage network in accordance with relevant standards. Scope of work includes, but is not limited to: Cutting of asphalt, excavation, preparation of subgrade, and disposal of surplus material.Construction of reinforced concrete surface drainage channels complete with heavy‑duty galvanized or ductile iron gratings suitable for fuel station vehicular loading. Supply and installation of the oil separator, including inlet and outlet connections, and all associated fittings. Concrete bedding, haunching, backfilling, compaction, and reinstatement of surrounding finishes. Connection of drainage channels to the oil separator and from the oil separator to the main drainage network. Oil separator capacity and final layout shall be presented for approval prior to commencement of any works on site. | LS | 1
29.8 | Installation of 3m high T walls on two sides of the fuel station. T walls will be provided and transported on site by EULEX. Contractor is to position them on site as per final designs for the fuel station. 43X1.5m T walls | LS | 1
29.9 | Provide and install steel angle impact barrier 500mm x 500x500, refer to technical specifictions for more details. | EA | 3
Total 29
To be provided by EULEX and Transported on site
Note: | Cabin/Office container
Fuel tank with containment tank and cover, fuel pump and RFID post
T walls
30 | Description | Unit | Quantity | Unit price | Total
Covered parkings and other works
30.1 | Provide material, manufacture and install metal cover for parking spots for larger vehicles - type "A" marked in layout - dim 27.5x7m , clear height 3m. Refer to technical specifications for details. | EA | 1
30.2 | Provision of materials and installation of metal cover for parking spots "B". For this cover EULEX will provide the steel structure with the required dimensions ( trusses/columns) . Contractor is to carry installation of the same, paint the structure provide and install prepainted sheets with gutters. Refer to technical specifications for details. dim 31.5x6m | EA | 1
30.3 | Provision of materials and installation of metal cover for parking spots "C". For this cover EULEX will provide the steel structure with the required dimensions. Contractor is to carry installation of the same, paint the structure and provide and install prepainted sheets with gutters. Refer to technical specifications for details. dim 6x6m | EA | 2
30.4 | Provide and install steel flag poles of 7.0 meters height above finished ground level complete with raising and lowering mechanism. The poles shall be manufactured from hot‑dip galvanized steel suitable for outdoor use and long‑term corrosion resistance. The flag poles shall be installed on properly designed concrete foundations sized to withstand prevailing wind | EA | 3
30.5 | Provide and install sink with cabinet 120x60cm for various kitchenettes in the Compoound , price to include water tap complete | EA | 12
Total 30

## Dismantling
Construction of New ECM - Design and Build Project
4.2.3 Breakdown - Dismantling of Container blocks and refurbishment of structure
31 | Description | Unit | Quantity | Unit price | Total
Dismantling of Container blocks and refurbishment of Containers' structures
31.1 | Dismantling of Container Block RN: Container block consist of 19 office containers of 20' (605x244cm) and 3 ablution units of 20' (605X244cm) as per drawing and pictures provided. The block is organised in ground plus first floor positioned over strip foundations and covered with a two slope roof. After dismantling container frames are to be made free of all wall panels, floor layers are to be dismantled as well, leaving only the ceiling of the same. Apart from assets which are to be handed over to EULEX Representative all other debris is to be removed from site and sent out to a designated municipal dump site. Note: Building envelope is styrofoam "demit" facade which is to be cut to split the containers and also detached. See technical specifications for all details of the building and works required . | LS | 1
31.2 | Dismantling of Container Block O1: Container block consist of 26 office containers of 20' (605x244cm) and 8 small ablution units (244x255),as per drawing and pictures provided. The block is organised in ground floor positioned over concrete blocks and covered with a two slope roof. After dismantling container frames are to be made free of all wall panels, floor layers are to be dismantled as well, leaving only the ceiling of the same. Apart from assets which are to be handed over to EULEX Representative all other debris is to be removed from site and sent out to a designated municipal dump site. Note: Building envelope is styrofoam demit facade which is t be cut to split the containers and also detached. See technical specifications for all details of the building and works required . | LS | 1
31.3 | For all containers of 20' clean the steel structure and repaint with antirust paint. Unit price per container. See technical specifications for details. | EA | 46
31.4 | For all containers of 10' listed above clean the steel structure and repaint with antirust paint. Unit price per container. See technical specifications for details. | EA | 4
31.5 | Provide and install galvanised metal sheet under the floor structure thickness = 0.8mm | m2 | 600
31.6 | Transporting of 20' containers from existing ECM to new ECM Compound, estimated around 4 km. See technical specs for more details. | EA | 46
31.7 | Transporting of 10' containers from existing ECM to new ECM Compound, estimated around 4 km. See technical specs for more details. | EA | 4
Total 31